## Slide 2: Project Management 101
The Return of…

## Slide 3: Schedule - Day 2
Agenda | Time | Notes
Recap | 10:00 am | Review Content + Takeaways from Session 1
Project Timelines | 10:30 am | Building Project Schedules + Introduction to Project Tools
Real Life Example: Part 4 | 11:45 am | Create a Project Schedule (GANT)
Lunch | 12:30 pm | 
Proposal Submissions | 1:30 pm | Overview of Project Proposal Submissions Process
Working on your own project idea | 2:00 pm | Opportunity to ask the instructor to review your project idea, proposal or charter
Break | 2:45 pm | Short Break, Q&A
Working on your own project idea | 3:00 pm | Opportunity to ask the instructor to review your project idea, proposal or charter
Wrap Up | 3:45pm | Session Wrap Up, Next Steps (Schedule webinar sessions for Asana & Basecamp)

## Slide 4: Recap: Day 1
Session 1 Knowledge Areas:
Project Concepts and Definitions, Characteristics and Roles
The Project Charter and Scope Documents
Work Breakdown Structure
Notes: Feedback from survey: traditional courses very dry, decided to teach a course more immersive

## Slide 5: Recap: Day 1
What is a Project?
  Temporary in nature
  Has a unique Product, Service or Result
  Coordinated undertaking of interrelated activities
Business Need
  What is driving the need to embark on this project?
Project Justification
  Business Case- On what financial or other basis can we justify doing this project?
  Tools: Cost/Benefit Analysis, Key Metrics
Notes: Business Need: A problem could have many solutions. Our Project is being carried out to deliver one such solution
Project Justification: Why is this solution the best?

## Slide 6: Recap: Day 1
Product Description/Deliverables
A tangible thing that results from the completion of the project
Could be
  A Product
  A Service
  An improvement initiative
  A result or decision
Notes: Business Need: A problem could have many solutions. Our Project is being carried out to deliver one such solution
Project Justification: Why is this solution the best?

## Slide 7: Recap: Day 1
Stakeholders
An individual, group, or organization, who may affect, be affected by, or perceive itself to be affected by a decision, activity, or outcome of a project”
Examples
  Project Sponsor – Commonly has budgetary approval for the project
  Project Manager – Responsible for meeting the requirements of the project
  Project Team – Collectively responsible for completing the project
  Customers – Beneficiaries of the deliverables of the project
  Performing Organization – Specific groups performing the work on the project
Notes: Stakeholders : People on neighboring island

## Slide 8: Recap: Day 1
The Triple Constraint
  Time
  Cost
  Scope

## Slide 9: Recap: Day 1
The Project Charter
A fundamental tool used to establish the Project
Succinctly defines key characteristics of the Project
Helps to orient new members of the team
Establishes the Identify of the Project and her respective Authority level
Use this tool to help craft your Proposals

## Slide 10: Recap: Day 1
The Scope Statement
Project Scope Description
Acceptance Criteria or what must be completed in order for the project to be considered a success
Deliverables which can be thought of as the end result of the project
Exclusions which typically identify the areas that are out of scope for the project
Constraints which are externally imposed restrictions on the project, such as deadlines, budgets and limited resources
Assumptions relating to the scope of the project and the potential impact of these assumptions if they are not valid.

## Slide 11: Recap: Day 1
Work Breakdown Structure (WBS)
Product Orientation: What do we need to build (not how)
All of the work that has to be performed on the project
Hierarchical in nature
Decomposition: Breaking down project deliverables into smaller, more manageable components
Work Packages (4-80 hours ~ depends?)
Notes: The WBS tells us what needs to be done.
The Activity list tells us how the work gets done
Analogy of Restaurant Menu
Handout:
Various cost estimates

## Slide 12: Getting Organized – Time and Cost

## Slide 13: Getting Organized – Time and Cost
What you will learn:
  Activity List and Duration Estimates
  Cost Estimates
  Scheduling work
Exercise: Creating a Project Schedule

## Slide 14: Getting Organized – Activities
Activity Definition
  Based on the WBS document
  What tasks must be performed in order to complete the WBS component
  Try to involve experts

## Slide 15: Getting Organized – Activities
Activity Duration Estimates
  How long does an Activity Take?
  Program Evaluation and Review Technique (PERT)
    Great if you have a lot of Data!
    Pessimistic: Worst Case Scenario
    Most Likely: Based on prior experience
    Optimistic: If everything goes well
  Benchmarking

## Slide 16: Getting Organized – Activities
Activity Sequencing
  Correct sequence of performing activities now that they have been defined
  Dependencies
    Mandatory: A physical or technological limitation of the work (Must do A before B)
    Discretionary: Historical/Organizational Preference

## Slide 17: Sequencing Tools
Network Diagrams
Activities on Nodes
Lines represent relationships
Movement Left > Right

## Slide 18: Getting Organized – Activity List
ID | Task Name | Duration | Assigned | Status
1 | Finalize List of Exhibitors | 24 | Pat | DONE
1.1 | Conduct Exhibitor Outreach Program | 16 |  | DONE
1.2 | Finalize Exhibit requirements | 8 |  | DONE
2 | Define Event Space | 40 | Barbara/John | In Progress
2.1 | Identify Space usage requirements | 8 | Barbara | DONE
2.2 | Identify potential layout plans | 16 | Barbara | In Progress
2.3 | Confirm Event Dates with Venue and Exhibitors | 8 | John | In Progress
2.4 | Obtain Permits from Town | 8 | John | In Progress
3 | Prepare Event Space | 100 | Joanne | Not Started
3.1 | Purchase Makerspace Equipment | 20 | Joanne | Not Started
3.2 | Finalize placement of Carts and Accessories | 20 | Joanne | Not Started
.. | .. | .. | .. | 
Notes: Note that we have copied the WBS coding scheme

## Slide 19: Project Schedules
Why use Schedules?
Schedules allow us to take a project list and apply it to a calendar
Allows us to incorporate real-world events (Public Holidays and Vacations)
Track project progress against dates and deadlines

## Slide 20: Project Schedules
Milestones
An activity of zero duration
Identified as being significant in the project
  End of a phase or task
  Delivery of a work result
  Expenditure of a certain amount of money

## Slide 21: GANTT Charts
Henry Gantt (1861-1919)
Used during the Hoover Dam and Interstate Highway System Projects
Depicts Activities, Dates and Resources

## Slide 22: Real Life Example: Project Schedule
In this exercise, we will examine the makerspace project and
60 minutes: Review the sample project proposals
15 minutes: Discussion

## Slide 23: Real Life Example - Takeaways
A visual tool is useful when trying to identify solutions to common issues that arise when managing projects
  Impact of a delay
  Resource conflict
  Date changes

## Slide 24: Getting Organized –Cost Estimates
Cost Estimate Type | Characteristics
Top-Down (Budgetary Estimates) | Benchmarking: Refer to reference projects, vendor estimates Short time to assemble Lower Accuracy
Bottom-Up (Detailed Estimates | Detailed Estimates Longer time to assemble Higher Accuracy

## Slide 25: Lunch
…need I say any more?

## Slide 26: 15 minute bonus: Running the Project
What you will learn:
  The Kickoff Meeting
  Task Assignment
  Monitoring Progress
  Closing out
Handout: Kickoff Meeting sample agenda

## Slide 27: Running the Project
The Kickoff Meeting
  Goals
    Get everyone aligned on the Project, it’s goals and objectives
    Formally establish the role of the PM
  Sample Agenda:
    Introduction
    Review of Project Charter
    Establish PM Standards
    Introduce Project team members
    Establish Project Communications Needs

## Slide 28: Running the Project
Assigning Work
    Work Authorization System:
      Formal approval of the work by relevant authorities
      Formal approval of the vendor or individual performing the work
      Detailed description of task, including success requirements and required skills
    Resource Assignment Matrix

## Slide 29: Running the Project
Status Meetings
Lasts less than an hour
Goes through ongoing project tasks
Methodical and organized format.
Agenda:
  Summary of Status
  Open Action Items
  Open Risks and Issues
  Closing the meeting

## Slide 30: Running the Project
Closeout
The Project Manager is responsible for tracking and recording the completion of completion of Deliverables, Phases or Milestones
How: Evaluation Criteria
Who: Sponsor/Owner Signoff

## Slide 31: Running the Project
Lessons Learned
Documenting anything that the project team learned during the project or a project phase that may benefit subsequent phases or project teams in the organization.
Documented and kept in a centralized repository where it can be accessed by other users and readily accessible
Organization is doomed to repeat the same mistakes unless it can find a way to document these lessons and transmit them to others who can benefit in the future.
Do not wait too long to do this!

## Slide 32: Appendix 1 - Agile
Great when you don’t understand the requirements up front
Building a bit and releasing in more frequent intervals
Waves of mini-iterations throughout project known as Sprints
Each sprint typically lasts 2-3 weeks

## Slide 33: Proposal Submissions
Summary (or problem statement or background)
Project scope
Stake holders including project manager and team
Timeline
Cost
Expected outcome
Benefits realized by the project
Notes: ​As a part of our workshop series, participants will manage a small project at their own library. We will subsidize $300 for each participating library, and the libraries might put some more budget to that. And, yes, the proposal is to obtain both budget/official sign off from LibraryLinkNJ and the participating library directors. Please note this will be a small project for participants to have an opportunity to manage a project based on what they learn through our series workshops.

## Slide 34: Knowledge Recap
The Charter | Document your Deliverables and Signoff Constraints > Imposed on the Project Assumptions > Write them down!
The WBS | Decomposition – That’s breaking things down The WBS elements
Time and Cost | Activity definition Activity Sequencing Task dependencies (Start to Finish, Finish to Start etc.)
Kicking Off | Kick off meeting Resource Leveling
Monitoring Progress | Project Cadence is everything Measure against your baselines
Wrapping Up | Obtain signoff, then move on Document Lessons learned quickly

## Slide 35: Conclusion
Class Evaluations (Please take a minute to fill in)
Additional Resources:
  Website link to download: http://www.samsena.com/PM-101-2018